## Sheet1
| Part Name | Part Number | Supplier | Quantity req. | Quantity held | Quantity to order | Lead time | Ordered | Complete | Shipped | Comments
Dogleg | Kapton dogleg | TW-version No? | CSIST/SCL | 2112 | samples | 2540 | 4w after materials | N | N | N | Start production assembly in April
| AlN heat spreader pieces | TW-drawing No? | Agate | 2112 | samples | >2500 | 4 weeks (tbc) | N | N | N
| AlN heat spreader assembly | ~ | SCL | 2112 | 0 | 2540 | SCL |  | N | N
| dogleg powertape plug | ASP-67876-01 | Samtec/Toby | 2112 | 60 | 2500 | 12 days | N | N | N
| dogleg module plug | FTS-118-01-L-DV | Samtec/Toby | 2112 | 60 | 2500 | 7 days | N | N | N | Need FTSH length pin?
| redundancy arm plug | 3-175642-6 | Amp/Flint | 2112 | 3550 | ~ | Ship after PRR |  |  | N | In tubes
| redundancy arm socket | 3-175636-6 | Amp/Flint | 2112 | 3550 | ~ | Ship after PRR |  |  | N | 2 reels and 600 loose
| C1 capacitor, 0402 10nF | CC0402CX7R103KTR | TDK/Flint | 2112 | 80 | 1 reel / 10K | stock | N | N | N
| C2 capacitor, 0603 100nF | CC0603CX7R104KTR | TDK/Flint | 2112 | 160 | 1 reel / 4K | 2 weeks | N | N | N
| R1&R3 resistor, 0402 100R | MCR01MZSF1000 | Rohm/Flint | 4224 | 50 | 1 reel / 10K | stock | N | N | N
| R2 resistor, 0402 1K | MCR01MZSF1001 | Rohm/Flint | 2112 | 50 | 1 reel / 10K | stock | N | N | N
| VDC | VDC | Mintech/AMS | 2112 | ~8000 | ~ | Ship after PRR |  | N | N | Radiation qualification 3 batches
| DORIC | DORIC4A | Mintech/AMS | 2112 | ~8000 | ~ | Ship after PRR |  | N | N | 1 batch/month
| chip cover | MLC-drawing No? | Oxford | 2112 | samples | 2540 | 4 weeks | N | N | N
Opto-package | opto housing | ~ | Radiantech | 2112 | ~ | ~ | ~ |  |  | N | Made by Radiantech In house
| VCSEL | TDS-8A12 | Truelight | 4224 | samples | ~20000 | 1 week post Qual. | N | N | N | Includes Fwd. Harness + 40%
| PIN diode | APEX10 | Centronic | 2112 | samples | 5720 | TW | wafer | N | N | Includes Fwd. Harness + 40%
| fibre | S-12T-50/60/125-R | Fujikura | 0.5km 12way | 119KM | ~ | Ship after PRR |  |  | N | 89km@CERN, 30km@Japan
| furcation tubing | CM | CM | 5.3KM | 100M | 7.4KM | CM | N | N | N
Fibre ribbon extension | fibre | S-12T-50/60/125-R | Fujikura | 2.1 km 12way | [5 empty] | N | See item under opto-package
| splice protector | MLC-drawing No? | Academia Sinica | 704 | samples | +704 | 100/day |  | N | N
| MT8 connectors | TW | TW | 352 | 1700 | ~ | Ship after PRR |  |  | N | At KEK
| MT12 connectors | TW | TW | 352 | 5000 | ~ | Ship after PRR |  |  | N | At KEK
| non-magnetic guide pins | TW | TW | 1408 | 6700 | ~ | Ship after PRR |  |  | N | At KEK
Powertape PCB | red powertape PCB | TW | Express circuits | 2112 | 0 | 2540 | 2 weeks | N | N | N | 20% spares
| solder screen | TW | Tecan | 2 | 0 | 2 | 1 week | N | N | N
| solder screen printing | ~ | Oxford | 2112 | 0 | 2540 | 1 week |  | N | N
| powertape PCB socket | CLP-119-02-L-DH | Samtec/Toby | 2112 | 70 | 2500 | 8 days | N | N | N
Powertapes | Al/Kapton sheet | Ljub/TW | GTS(UK) | Ljub | 0 | TW xxx m2 | 6 weeks | N | N | N | 25 or 50uM to be decided
| Cover layer | TW | GTS(UK) | TW | 0 | TW xxx m2 | 10 weeks | 2001-12-13 | N | N
| Production of tapes | ~ | Ljubljana | 2112 | 0 | ~2540 | See Ljub Schedule |  | N | N | Start March 02
| Aluminised Kapton shielding | 660190Al | GTS | 228.8M | 125M x 305mm | TW/CM | TW | N | N | N | Require width ~60mm, waiting for test
| temporary clips | JF-Drawing No? | Oxford/Taiwan | 3520 | samples | TW | TW/MLC | N | N | N
PP1N | PP1N | Ljub | Ljubljana - JSI | 352 | 0 | 430 | Ljub | N | N | N
| 240 pin plug | 53475-2409 | Molex | 2112 | 32 | 2540 | Ljub | N | N | N
| 4.7 uF capacitor | Ljub | Ljub | 4224 | Ljub | Ljub | Ljub | N | N | N | purchase for forward at same time
| 1 uf capacitor | Ljub | Ljub | 4224 | Ljub | Ljub | Ljub | N | N | N | purchase for forward at same time
| 15 nf capacitor | Ljub | Ljub | 2112 | 5000 | ~ | Ljub | N | N | N
| PP1N assembly | ~ | Elgo Line | 352 | 0 | 430 | 3 weeks | N | N | N
| powertape clamp | ~ | RAL OM group | 352 | 0 | 430 | 4 weeks | N | N | N
Redundancy link | Kapton link | TW | TW | 176 | 0 | TW | TW | N | N | N
| redundancy arm plug | 3-175642-6 | Amp/Flint | 176 | 3550 | ~ | Ship after PRR |  |  | N
| redundancy arm socket | 3-175636-6 | Amp/Flint | 176 | 3550 | ~ | Ship after PRR |  |  | N
Consumables | Boron Ni adhesive | 2011/AC PT140S | Ciba-Geigy
solder paste
| UV curing glue | OG-124 | Epotek
| epoxy | 353ND | Epotek
| conductive epoxy | H20E | Epotek
Al bonding wire
| ribbonising adhesive | S-611-04 | Fitel
| Kapton tape | 3M/? | [8 empty] | Awaiting Radiation qualification