Supply of low-mass tapes for the ATLAS SCT detector

TENDER FORM

(two copies to be returned duly completed, signed and dated)

BIDDER

Name

Address

Telephone

Fax

E-mail

NAMES OF THE PERSONS IN CHARGE OF THIS TENDER:

| Commercially | …………………… | Tel.: | …………… | Mobile: | ……………… |
| --- | --- | --- | --- | --- | --- |
|  |  | Fax: | …………… | E-mail: | ……………… |
| Technically | …………………….. | Tel.: | …………… | Mobile: | ……………… |
|  |  | Fax: | …………… | E-mail: | ……………… |
|  |  |  |  | Date: | ……………… |

Table of Contents

1	CONFORMING BID AND ALTERNATIVE PROPOSALS BY BIDDERS	3

2	GENERAL INFORMATION	4

3	TOTAL FIRM PRICE FOR COMPLETE SUPPLY	5

4	PURCHASE OPTION	7

5	PAYMENT CONDITIONS	7

6	DELIVERY SCHEDULE	9

7	PENALTY FOR LATE DELIVERY	9

8	PROVISIONAL ACCEPTANCE	10

9	FORCE MAJEURE	11

10	CONTRACT TERMINATION	12

11	DOCUMENTS TO BE ATTACHED TO THE TENDER	12

12	COMPLIANCE WITH THE TECHNICAL SPECIFICATION	13

13	GOVERNING LAW AND ARBITRATION	13

14	REMARKS IF ANY	14

# CONFORMING BID AND ALTERNATIVE PROPOSALS BY BIDDERS

## Bidders are required to submit a bid on this Tender Form, using indelible ink or a typewriter. Bids shall be based on the Tender documents included in this Invitation to Tender (subject to any Addenda issued) without any variation or alternative to the Tender documents, including but not limited to the General Conditions of Contracts, this Tender Form and the Technical Specification.

## Any Bidder wishing to offer an alternative proposal, whether technical or otherwise must also submit a Conforming Bid. If technical or other additional alternatives are offered in addition to a Conforming Bid then such alternatives must be accompanied by all information (including, without limitation, technical and financial) to enable a complete evaluation of the alternative. The Bidder shall indicate in his Tender any increases or deductions in the total Ex-Works price of the Conforming Bid that would result from the acceptance of any alternative proposal.

## Only the alternatives, if any, submitted by the Bidder who has submitted the lowest Conforming Bid shall be considered and it shall be at sole discretion whether to accept the Conforming Bid, or the alternative submitted by that Bidder, regardless of the result of the comparative evaluation. Bidders must therefore be prepared to enter into a Contract on the basis of their Conforming Bid notwithstanding any alternative proposed.

# GENERAL INFORMATION

## This Tendering action is being conducted by the “Jožef Stefan” Institute in Ljubljana, Slovenia. After the selection of the successful Bid a Contract will be placed by the European Organization for Nuclear Research, based in Geneva, Switzerland, on behalf of the ATLAS Collaboration. The Contract will be sublject to General Conditions of CERN Contracts (CERN/FC/1814-II).

## The scope of this Invitation to Tender is the manufacture and supply of low-mass tapes for the ATLAS SCT detector and corresponding spare parts (hereafter referred to as the “Supply”), for the ATLAS Experiment.

## The Bidder/Contractor shall be liable for any information prepared by or on his behalf, and for the use in accordance with professional standards of any information provided to him under the Invitation to Tender and the Contract.

## Where the Contractor seeks any approval or agreement of CERN or any other party, the giving of such approval or agreement shall not release him from his obligations or liabilities under the Contract.

# TOTAL FIRM PRICE FOR COMPLETE SUPPLY

The Bidder shall indicate net and firm prices, not subject to revision, exonerated from all taxes and customs duties, drawn up in accordance with the provisions stipulated in the Invitation to Tender.

| TOTAL PRICE IN SWISS FRANCS DDU Academia Sinica, Taiwan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Item | Description | Pos. | Length / mm | QTY / pcs | Price / unit | Total |
| 1 | Low mass B-tapes, 2640 pcs in the following lengths |  | 860 | 140 |  |  |
|  |  |  | 908 | 60 |  |  |
|  |  |  | 979 | 90 |  |  |
|  |  |  | 1014 | 100 |  |  |
|  |  |  | 1085 | 40 |  |  |
|  |  |  | 1145 | 150 |  |  |
|  |  |  | 1193 | 60 |  |  |
|  |  |  | 1236 | 70 |  |  |
|  |  |  | 1276 | 120 |  |  |
|  |  |  | 1307 | 140 |  |  |
|  |  |  | 1345 | 100 |  |  |
|  |  |  | 1393 | 150 |  |  |
|  |  |  | 1441 | 150 |  |  |
|  |  |  | 1488 | 140 |  |  |
|  |  |  | 1546 | 160 |  |  |
|  |  |  | 1582 | 140 |  |  |
|  |  |  | 1627 | 100 |  |  |
|  |  |  | 1661 | 90 |  |  |
|  |  |  | 1698 | 80 |  |  |
|  |  |  | 1769 | 110 |  |  |
|  |  |  | 1840 | 110 |  |  |
|  |  |  | 1909 | 80 |  |  |
|  |  |  | 1945 | 100 |  |  |
|  |  |  | 2016 | 80 |  |  |
|  |  |  | 2085 | 80 |  |  |
| Sub-Total B-tapes |  |  |  |  |  |  |

| Item | Description | Pos. | Length / mm | QTY / pcs | Price / unit | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 2 | Low mass B-tapes, 2470 pcs in the following approximate lengths |  | 1880 | 130 |  |  |
|  |  |  | 1850 | 230 |  |  |
|  |  |  | 2240 | 230 |  |  |
|  |  |  | 2580 | 330 |  |  |
|  |  |  | 2950 | 330 |  |  |
|  |  |  | 3050 | 330 |  |  |
|  |  |  | 3250 | 330 |  |  |
|  |  |  | 3410 | 330 |  |  |
|  |  |  | 3500 | 230 |  |  |
| Sub-Total F-tapes |  |  |  |  |  |  |

CERN reserves the right to place the Contract in two parts, first for B-tapes, then for F-tapes, and to modify the above-mentioned quantities by ± 30%. CERN will provide the Contractor with the exact quantities before placing the Contract. The unit prices shall remain unchanged.

# MATERIALS SUPPLIED TO CONTRACTOR

Jožef Stefan Institute and ATLAS SCT UK (herein referred to as the “ATLAS SCT”) will supply free of charge to the Contractor the material as specified in Article 2.1 of the Technical Specification (herein referred to as the “Material”) for a total value of approximately 75000 CHF. All costs incurred for this supply, except duties and taxes, up to the Contractor’s premises shall be borne by ATLAS SCT.

Whenever customs formalities are necessary on importation into the country where the Contractor’s premises are located, these shall be carried out by the Contractor, including any advance requests for authorization concerning temporary importation and the provision of any customs bond as may be required.

The Contractor shall perform an incoming inspection of the Materials. In case of damage or a non conformity with their technical specification, the Contractor shall notify CERN in writing within 10 working days after their receipt of such damage or non-conformity and CERN will at its own choice either repair or replace the defective or non-compliant Materials free of charge for the Contractor. The Contractor shall not be liable for any delay incurred in so far as it has resulted from any such replacement or repair it being understood that this shall be the sole entitlement by the Contractor in such circumstances.

The Contractor shall use the Material exclusively for the performance of his obligations under the Contract.

The Contractor shall be solely responsible for the Materials, and shall at his own cost and in accordance with professional standards maintain, and if lost or damaged, replace or repair the same. He shall notify CERN forthwith in writing of any replacement or repair carried out on the Materials.

Forthwith upon completion of the use under the Contract, or upon termination of the Contract if earlier, the Contractor shall return any remaining Materials to the Jožef Stefan Institute. He shall be liable for any use of Materials in excess of that agreed, but shall not be liable for normal degradation of the Materials.

In the case where the Contractor needs more Material for the execution of the Contract than the quantity provided, he shall request CERN and no other party to procure and supply such Material. The cost for additional Material for the basic Supply shall be borne by the Contractor, that for purchase options by the ATLAS SCT.

# STORAGE

The Contractor shall provide storage for the period starting from the provisional acceptance of the Material until end of June 2004.

Notwithstanding the transfer of title from the Contractor to CERN upon provisional acceptance and payment thereof, the Contractor shall be solely responsible for the Supplies and their storage, until end of June 2004. To this end, the Contractor shall maintain at his own cost and in accordance with professional standards the Material, and if lost or damaged, replace or repair the same.

# PURCHASE OPTION

CERN reserves the right to place a purchase order option for additional quantities of the basic supply until end of June 2004. Additional quantities of tapes may be ordered during this period at the same cost as for the original order. The order for each tape length, when not exceeding 24 tapes, must come in multiples of 8 tapes. The total number of tapes for each of the additional orders must exceed 40 tapes. If Material, as specified in Article 5, is not sufficient to fulfil the additional order, ATLAS SCT shall supply the missing Material to the Contractor free of charge.

These prices shall be net and firm, not subject to revision, exonerated from all taxes and customs duties for purchase options placed before 30 June 2004.

.

# PAYMENT CONDITIONS

## The total amount of the Contract will be paid according to the following provisions:

### 100% (hundred per cent) of the value of each batch, 30 (thirty) days after provisional acceptance of the corresponding batch and receipt of a correct invoice in duplicate.

6.1.3	Any outstanding payment will be paid after provisional acceptance of the last batch and receipt of a correct invoice in duplicate.

# DELIVERY SCHEDULE

The Contract is to be placed for two positions: B-tapes and F-tapes. The provisional delivery schedule for B-tapes is:

| Delivery batches B-tapes | Contents Batch 1 | Contents Batch 2 | Contents Batch 3 | Contents Batch 4 | Contents Batch 5 | Contents Batch 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Delay after Contract | 6 weeks | + 2 weeks | + 4 weeks | + 4 weeks | + 4 weeks | + 4 weeks |
| Pos. no. B-tapes | tapes | tapes | tapes | tapes | tapes | tapes |
| 1 |  |  | 140 |  |  |  |
| 2 |  |  |  | 30 | 30 |  |
| 3 |  |  | 70 |  |  | 20 |
| 4 |  |  |  | 100 |  |  |
| 5 |  |  |  |  | 30 | 10 |
| 6 |  |  | 140 |  |  | 10 |
| 7 |  |  |  | 30 | 30 |  |
| 8 |  |  |  |  | 60 | 10 |
| 9 |  |  | 70 |  |  | 50 |
| 10 |  |  |  | 100 |  | 40 |
| 11 | 40 |  |  |  | 60 |  |
| 12 |  | 40 | 70 |  | 30 | 10 |
| 13 |  |  |  | 100 |  | 50 |
| 14 | 40 |  |  |  | 60 | 40 |
| 15 |  | 40 | 70 |  | 30 | 20 |
| 16 |  |  |  | 100 |  | 40 |
| 17 |  |  |  |  | 60 | 40 |
| 18 | 40 | 40 |  |  |  | 10 |
| 19 |  |  |  |  | 30 | 50 |
| 20 | 40 |  |  |  | 30 | 40 |
| 21 |  | 40 |  |  | 30 | 40 |
| 22 | 40 |  |  |  |  | 40 |
| 23 |  | 40 |  |  | 60 |  |
| 24 |  |  |  |  |  | 80 |
| 25 | 40 | 40 |  |  |  |  |
| Total in batch | 240 | 240 | 560 | 460 | 540 | 600 |

The delivery of F-tapes shall be in 6 batches, the first two batches of approximately 10 %, the remaining of 20 % of the respective total quantity. The first batch will be shipped 6 weeks after placement of the Contract for F-tapes, but not sooner than two weeks after the shipment of the last B-tape batch. The interval between batches is 2 working weeks for 10 % batches and 4 working weeks for 20 % batches. Two weeks spanning Christmas and New Year do not count as working weeks, as well as two weeks in July or August, specified by the contractor.

Does the Bidder agree with this delivery schedule?

| YES |  | NO |  |
| --- | --- | --- | --- |

If not, please comment:

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

# PENALTY FOR LATE DELIVERY

## For each complete week of delay following the contractual delivery schedule (see Tender Form, Article 8), CERN reserves the right to apply a penalty of 1% (one per cent) of the value of the Contract, except in case of Force Majeure (see Tender Form, Article 11).

## It is nevertheless understood, that the penalty shall be limited to a maximum of 5% (five per cent) of the total amount of the Contract.

## Upon reaching this maximum amount, CERN reserves the right terminate the Contract forthwith. Penalties and termination are without prejudice to other rights and remedies CERN may have under the Contract or otherwise.

# PROVISIONAL ACCEPTANCE

## Prior to shipment of each batch to Academia Sinica, the Contractor shall send to the Jožef Stefan Institute the Protocol of the Test Results according to Sections 2.2 and 4 of the Technical Specification. Upon their receipt Jožef Stefan Institute will verify its compliance with the Contract including the Technical Specification.  Jožef Stefan Institute reserves the right to carry out its own tests according to Section 4 on any portion of the produced tapes and the accompanying test structures to validate the Protocol of the Test Results. Academia Sinica, Taiwan, shall sign off acceptance of delivered tapes upon arrival. Jožef Stefan Institute and Academia Sinica shall notify CERN of their findings not later than two weeks after shipment or arrival date, respectively.

## In case CERN deems that the Protocol of the Test Results of the Batch concerned do not fully comply with the Contract including Technical Specification, the provisions of Article 10 hereunder shall apply.

## In case CERN deems that the Protocol of the Test Results of the Batch concerned do fully comply with the Contract including Technical Specification, he shall so notify the Contractor.

## If CERN has not declared provisional acceptance nor notified the Contractor of any non-conformity, within 1 (one) month of the date of receipt of each Batch at Academia Sinica, the latter shall be deemed to have been accepted by CERN.

# FORCE MAJEURE

If either party is prevented, wholly or in part, from performing its obligations under this Contract as a result of Force Majeure, then that party shall be relieved from all liability in respect of any delay or failure in the performance of such obligations during the continuance of the Force Majeure in so far as the same are affected by Force Majeure.

Force Majeure means any circumstance beyond the reasonable control of the party claiming relief such as, but not limited to, acts of nature, fire or war.

A default or delay of suppliers or subcontractors of one of the parties as well as a strike or other labour conflict of a party or its supplier/subcontractor shall not constitute a case of Force Majeure (except in cases of nation-wide conflicts).

The party whose obligations are affected by a case of Force Majeure shall notify the other party without delay and give reasonably full particulars and indication of the probable duration of the Force Majeure.  It shall notify the other party immediately when the Force Majeure situation has ceased.

The time for the performance of the contractual obligations affected by Force Majeure shall be extended for the duration of Force Majeure, it being understood that the party whose performance is affected shall use all reasonable efforts to minimise the consequences of such failure.

Should the Force Majeure situation extend beyond 5 (five) months, the party not affected by Force Majeure shall have the right to terminate the Contract with immediate effect. In case of such termination all costs related thereto shall be shared equitably between the parties.

# CONTRACT TERMINATION

## CERN reserves the right to terminate the Contract under any of the following conditions:

### If the Supply does not comply fully with the requirements of the Contract including the Technical Specification. In this case, CERN shall advise the Contractor in writing of the non-conformity whereupon the Contractor shall forthwith and at his own cost take such steps as are necessary to ensure conformity of the supply. In case corrective action leading to the conformity of the supply has not been taken within six weeks from the date of notification, CERN reserves the right to terminate the Contract forthwith.

### In case the delivery schedule, as stipulated in Article 6 above, not being respected and after the maximum penalties, as stipulated in Article 7 above, have been reached, CERN reserves the right to terminate the Contract.

## In the event of a termination in accordance with sub-Article 14.1, the Contractor shall hold CERN free and harmless of any losses and damages including costs arising from this termination.

## In the event of such termination, CERN’s only obligation to pay shall be limited to those supplies which have been provisionally accepted, without any indemnity whatsoever including payments for any non-conforming supplies or costs incurred by the Contractor for raw materials, specific investments or specific tooling.

# DOCUMENTS TO BE ATTACHED TO THE TENDER

- All documents in accordance with the Technical Specification.

- Any other relevant information.

# COMPLIANCE WITH THE TECHNICAL SPECIFICATION

Does the Supply proposed by the Bidder comply with the enclosed Technical Specification in all respects?

| YES |  | NO |  |
| --- | --- | --- | --- |

If not, indicate the exceptions.

# GOVERNING LAW AND ARBITRATION

In conformity with the provisions stated in Articles 32, 33 and 35 of the General Conditions of CERN Contracts (CERN/FC/1814-II).

# REMARKS IF ANY

I, the undersigned, hereby declare that I have read the documents and clauses relating to the present Invitation to Tender and, if awarded the Contract, undertake to carry out the work required according to normal trade practice within the prescribed time limits, and at the price set out in the present Tender Form.

Date ...................................................

Signature and stamp of firm:

NB: Any corrections, erasures or other form of alteration herein shall be initialled by the Bidder.